# Reeves Intelligence: 90-Day Marketing Plan

Starting point: pre-revenue, a 20,000-contact researched (cold) nonprofit list, $0 ad budget, 25+ founder hours/week, three tiers (Core $2,388/yr · Pro $4,788/yr · Max $10,788/yr), 7-day free trial, and a walkthrough demo.

The 90-day goal: get the first paying customers, learn the real conversion numbers, and build the channels that can reach $1M in annual recurring revenue (ARR).

# 1. The honest math

$1M ARR ≈ 286 customers at an assumed average of $3,500/yr (mostly Core, some Pro and Max).

Cold email alone, over about 45 sending days (after 2–3 weeks of inbox warm-up):

| Scenario | Contacts reached | Positive replies | Trials (40% of replies) | Paying (25% of trials) | ARR at $3,500 avg |
| --- | --- | --- | --- | --- | --- |
| Base: 5 inboxes × 40/day, 2% reply | 9,000 | ~180 | ~72 | ~18 | ~$63k |
| Strong: 10 inboxes × 45/day, 4% reply | 20,000 (whole list) | ~800 | ~320 | ~80 | ~$280k |

These rates are assumptions, not proof. Replace them with real numbers after the first 2–3 batches.

Conclusion: $1M ARR in 90 days from cold email to one list is very unlikely, and a plan that promised it would be lying to you. Even the strong scenario falls short of $1M, and the list can only be emailed once. To close the gap you need channels that reach many nonprofits at once (partners) and bigger deals (Max tier). This plan builds both.

90-day targets:

Floor: 20 paying customers, about $60k ARR, and a proven reply → trial → paid funnel

Target: 50 customers, about $175k ARR, at least one partner channel live

Stretch: 80+ customers, $280k+ ARR, and a clear path to $1M ARR within about 12 months

# 2. The five engines

## Engine 1: Cold email to the researched list (the main engine)

Runs on YAMM with outreach/cold-sequence-v1.md.

Separate sending domain, 5 Workspace inboxes to start, and 10 once numbers justify it

Batches of about 200 per tab, best-fit segments first: small, grant-dependent organizations, contacts who are executive directors or development staff

A/B test email 1A (demo link) against 1B (no link, "want me to send it?")

Bottleneck: your time. Every reply needs a fast, personal response, and 800 replies won't fit into 25 hours a week. Use Reeves itself to produce Fit Checks quickly, keep reply templates, and plan to add hours or a part-time helper by month 2 if replies come in

## Engine 2: Partners (the only fast way to reach many organizations with $0 in ads)

One partner can put Reeves in front of hundreds of nonprofits at once. Targets:

State nonprofit associations in West Virginia and California: member webinars, newsletter features, member discounts

Community foundations in your two regions: they want their grantees to win more outside funding

Freelance grant writers and grant consultants: each serves many clients. They're natural Pro or Max users, and a referral commission can turn them into a sales force

Fiscal sponsors and nonprofit capacity-building programs

Offer partners a free live workshop for their members on "How to tell if a grant is worth applying for, before you write a word." Teach it genuinely (give away your best stuff) and show Reeves at the end.

## Engine 3: Bigger deals (Max tier)

Ninety-three Max customers equals $1M ARR on its own. Build a separate, smaller list of larger Los Angeles nonprofits with development teams of 5–15 people. Approach them with personal 1:1 outreach and a live demo instead of mail merge, since the high-touch onboarding is part of what they're paying for.

## Engine 4: Build your own opted-in list

The cold list can only be emailed once. Your own list keeps working for years.

Put a lead magnet on getreeves.ai: "The Grant Fit Checklist: know whether a grant is worth applying for before you write a word." Use a simple squeeze page: headline, one sentence, an email field, nothing else

Ask everyone who replies, takes a trial or attends a workshop whether they'd like to join

After signup: deliver the checklist, then send 3–4 warm-up emails with your best advice

## Engine 5: Founder content on LinkedIn ($0)

Executive directors and grant writers are on LinkedIn. Post 3 times a week, each post answering one real question prospects ask you (keep a running log of those questions). Every post points to the Grant Fit Checklist.

# 3. The founding-member offer (decide before week 3)

You can't show testimonials yet, so be honest and make the risk small:

"Reeves is new. We're looking for our first [25] founding nonprofits. You get [founding price locked for life / free high-touch onboarding / X months free on annual], and in return we ask for honest feedback."

A guarantee: [e.g. 30-day money-back on annual plans], to decide

Push annual plans: they bring cash in upfront, and founding pricing is a good reason to prepay

# 4. Week-by-week

## Month 1: foundation and first customers

Week 1

Register the sending domain, create the inboxes, set up SPF, DKIM and DMARC, and start warm-up

Verify the first 2,000 addresses and fill in MissionLine for the first 1,000 (Claude can help in bulk)

Decide the founding offer and guarantee

Pick the 50 best-fit prospects and email them 1:1 from your normal inbox. This is personal email, not a mail merge, so no warm-up is needed

Week 2

Build the Grant Fit Checklist and its squeeze page

List 20 partner targets (associations, foundations, grant consultants) and reach out to the first 10

Write the trial welcome emails. Their job is to get each user to see Reeves assess a real grant on day 1

Start LinkedIn posts, 3 a week

Weeks 3–4

Start YAMM batches at 20–30/day per inbox and ramp up

Do Fit Checks within 24 hours of every "yes"

Aim for 5 paying customers by day 30

Book the first partner workshop

## Month 2: scale what works

Get YAMM to full volume and pick the winner of email 1A vs. 1B

Run 1–2 partner workshops

Start Max-tier 1:1 outreach to larger Los Angeles nonprofits

Collect real feedback from founding customers, and ask permission before quoting anyone

Add a referral ask: "Know another organization that would find this useful?"

Add hours or help if replies exceed your capacity

Aim for 20 customers by day 60

## Month 3: double down

Put more volume into the best segment and region; add inboxes if the numbers justify it

Write the first real case study, with the customer's permission and real numbers only

Start regular emails to your opted-in list, alternating useful emails with offers

Run the first offer week (open Wednesday, close Sunday) to trial users who haven't bought and to your opted-in list

Sign at least one ongoing partner (a referral agreement or member discount)

Aim for 50 customers by day 90, then plan the next 90 days from real numbers

# 5. Weekly scoreboard (track every Friday)

| Metric | Why it matters |
| --- | --- |
| Emails sent | Are you hitting volume? |
| Bounce rate (keep under 3%) | List quality; protects your domain |
| Positive replies and reply rate | Is the message working? |
| Fit Checks and demos delivered | Your time bottleneck |
| Trials started | Top of the paid funnel |
| Trial → paid rate | Is the product proving itself in 7 days? |
| New customers, by tier | Revenue |
| ARR | The number that matters |
| Partner conversations and workshops | The channel that reaches many organizations at once |
| Opted-in list size | The asset you own |

# 6. Budget

Ads: $0, per plan

Tools: a small monthly spend is unavoidable: sending domain, Google Workspace inboxes, a YAMM paid plan, and email verification. Roughly $100–$250/month to start; check current pricing

Once there's revenue: reinvest in more inboxes, part-time help with replies, and eventually retargeting ads to people who visited the site or watched the demo

# 7. Rules that don't bend

Never fabricate testimonials, numbers or competitor claims (see business/reeves-intelligence.md)

The founder story stays on hold until the founder shares it

Stop emailing anyone who opts out, everywhere and permanently

Judge by replies and clicks, not opens